## Foreword
Foreword
This template is intended for those that generate, complete and review Task Information Delivery Plans. (TIDP) It is based upon the Construction Project Information eXchange (CPIx) BIM Execution Plan (BEP) template and guidance given in PAS 1192:2 +A2:2016.
The tables have some values pre-populated, these are for demonstration purposes only.
The lists of values are based on the guidance given in the CIBSE guidance note DE3 - BIM Execution Plans, but may not be sutable for a particular project. The TIDP has been created so that these values may be changed as appropriate.
This has been created with Building Services engineers in mind, but is adaptable to any construction discipline.
To assist the user, conditional formatting is applied to all numbers to ensure that they are not repeated in the worksheet. The value in column E (Type) should be different for each worksheet according to the following table:
  Table 3: DR
  Table 4: M2 or M3
  Table 5: SP
  Table 6: CA
Other tables may be created as needed by making copies of similar tables.
Template use
This template may be used to construct a TIDP. This in turn can be combined with other team member TIDPs to form a Master Information Delivery Plan (MIDP), which should appear in the Post-contract BIM Execution Plan.
The template should be used in the following way:
  Drawing Schedule:
  Edit Table 1 to show values that reflect the project.
  Edit the picklists columns A, B, C and H to values that reflect the project.
  Enter the milestone dates and descriptions in Table 2 to reflect the values shown in the Employer's Information Requirements or BIM Execution Plan, whichever has primacy.
  Add the drawings that you plan to create in Table 3. Select the Titles from columns I and J to assign values to columns F and D respectively. These values may be overridden by typing over the values suggested.
  Select the Zone (column C) and the Role (column F) to complete the drawing number.
  You can now complete the drawing titles in columns K, L and M.
  Select the milestone dates for when the drawings are to be issued.
  Other Schedules:
  Complete columns C, D, E, F and G using either the drop-down boxes or entering values, as appropriate.
  Add a descriptive title to the cell in column I.
  Select the milestone dates for when the documents are to be issued.

## Index
Index of Tables
Table 1 | Project Details
Table 2 | Milestone Dates
Table 3 | Drawing Schedule
Table 4 | Model Schedule
Table 5 | Specification Schedule
Table 6 | Calculation Schedule
picklists | Lists of lookup values

## Table 1 - Project Details
Table 1 – Project Details
Project Ref: | Project Name | Originator | Zones | Levels | File Types | Roles
PRO001 | Example Project | CIB | 00 | 00 | DR | EX
|  |  | XX | 10 | SC | MX
|  |  | ZZ | 20 | SK | PX
|  |  |  | 30 | SH | XX
|  |  |  | 40 | SP
|  |  |  | 50 | M2
|  |  |  | 60 | M3
|  |  |  | XX | CA
ZZ

## Table 2 - Milestone Dates
Table 2 – Milestone Dates
Milestone | Date | Desciption
Milestone 1 | 2016-08-17 | Brief
Milestone 2 | 2016-09-09 | Concept Design
Milestone 3 | 2016-09-30 | Detail Design
Milestone 4 | 2016-10-14 | Tender Issue
Milestone 5 | 2016-10-28 | Construction Issue
Milestone 6 | 2016-11-11 | Handover

## Table 3 - Drawing Schedule
Table 3 – Drawing Schedule
Project Ref: | Originator | Zone | Level | Type | Role | Number | Drawing Number | Title Line 1 | Title Line 2 | Title Line 3 | Title Line 4 | Title Line 5 | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
PRO001 | CIB | 00 | 10 | DR | MX | 50010 | PRO001_CIB_00_10_DR_MX_50010 | Mechanical General | Ground Floor | General Arrangement
PRO001 | CIB | 00 | 20 | DR | MX | 50020 | PRO001_CIB_00_20_DR_MX_50020 | Mechanical General | First Floor | General Arrangement
PRO001 | CIB | 00 | 10 | DR | EX | 60010 | PRO001_CIB_00_10_DR_EX_60010 | Electrical General | Ground Floor
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A
PRO001 | CIB |  | #N/A | DR |  | #N/A | #N/A

## Table 4 - Model Schedule
Table 4 – Model Schedule
Project Ref: | Originator | Zone | Level | Type | Role | Number | Model Number | Name | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
PRO001 | CIB | 00 | ZZ | M3 | XX | 00001 | PRO001_CIB_00_ZZ_M3_XX_00001 | MEP Model
PRO001 | CIB | 00 | XX | M2 | MX | 50001 | PRO001_CIB_00_XX_M2_MX_50001 | Mechanical Schematic Model
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____
PRO001 | CIB | [5 empty] | PRO001_CIB_____

## Table 5 - Specs schedule
Table 5 – Specification Schedule
Project Ref: | Originator | Zone | Level | Type | Role | Number | Specification Number | Name | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
PRO001 | CIB | 0 | XX | SP | EX | 00001 | PRO001_CIB_00_XX_SP_EX_00001 | Electrical Specification
PRO001 | CIB | 0 | XX | SP | MX | 00001 | PRO001_CIB_00_XX_SP_MX_00001 | Mechanical Specification
PRO001 | CIB | 0 | XX | SP | PX | 00001 | PRO001_CIB_00_XX_SP_PX_00001 | Public Health Specification
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__
PRO001 | CIB | 0 | XX | SP |  |  | PRO001_CIB_00_XX_SP__

## Table 6 - Calculation Schedule
Table 6 – Calculation Schedule
Project Ref: | Originator | Zone | Level | Type | Role | Number | Calculation Number | Name | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6
PRO001 | CIB | 00 | XX | CA | EX | 00001 | PRO001_CIB_00_XX_CA_EX_00001 | Electrical Loads Calc
PRO001 | CIB | 00 | XX | CA | MX | 00001 | PRO001_CIB_00_XX_CA_MX_00001 | Mechanical Heat Gain Calc
PRO001 | CIB | 00 | XX | CA | PX | 00001 | PRO001_CIB_00_XX_CA_PX_00001 | Rainfall Intensity Calc
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__
PRO001 | CIB | 00 |  | CA |  |  | PRO001_CIB_00__CA__

## Picklists
Mechanical General | 50 | Foundation Level | 00 | Drawing | DR | Delimiter | _
| 51 | Ground Floor | 10 | Schedule | SC
| 52 | First Floor | 20 | Sketch | SK
Domestic Water | 53 | Second Floor | 30 | Schematic | SH
Gas Supply | 54 | Third Floor | 40 | Specifiction | SP
Space Cooling | 55 | Fourth Floor | 50 | 2D Model | M2
Space Heating | 56 | Roof Level | 60 | 3D Model | M3
Ductwork | 57 | No Level | XX | Calculation | CA
Other Services | 58 | Multiple Levels | ZZ |  | 0
| 59 |  | 0 |  | 0
Electrical General | 60 |  | 0 |  | 0
Electrical Supply | 61 |  | 0 |  | 0
Power | 62 |  | 0 |  | 0
Lighting | 63 |  | 0 |  | 0
Communication | 64 |  | 0 |  | 0
| 65 |  | 0 |  | 0
Vertical Transportation | 66 |  | 0 |  | 0
| 67 |  | 0 |  | 0
Security and Fire Alarms | 68 |  | 0 |  | 0
| 69 |  | 0 |  | 0